## Assumptions - Concerns
Assumptions:
CW Services, Assett Services and Satelite Office: These sies will be supported remotely.
Detail Remote Support: Service Desk and Site Services Techs will use Team Viewer or GoTo Assist
Detailed Migration including user names and location
Genius Bar and Floor Walker are not realistic for CW Services scope. Some users are are inbedded at customer sites (Genentech, Yahoo, etc.)
Existing schedule includes multiple major market at the same time. Genius Bar staffing will be inadequate.
This is a living documents and for us to discover any short comings we will feedback from the Project Unity and Site Services teams from ongoing migrations.
Concerns/Questions:
Do we know if Team Viewer is on those CW Services machines?
Do we have an alternative to connect CW Service machines, if Team Viewer is not the tool?
Are the TekSystems resources only for Unity?
Where is everyone else regarding get TekSys resources?
Is there a way we can reshape the Unity schedule? CW Services part: Not spreading the resources across the region.
Because we could leave the skeleton crew in other parts we force on a major market
Is there a report that can identified failed/succedful migrations?
Can Project Team provide a list of user that have a copy of Office 2016?

## Day In The Life - Floor Walkers
Day In The Life - Floor Walkers
Time | Owner | Pariticpants | Action
7:00am | Territory lead | Project Rep | Morning Huddle
|  | Floor Walkers | Review previous days issues & workarounds/resolutions
Address "unique" configurations.
|  | Service Desk Rep | Review failed migration lists
Hand outs to floor walkers
Review migrated user schedule
Location list of migrated users by floor segment
Mark/Highlight users that have been migrated (floor plans are being gathered)
Assign end users to floor walkers **** note - floor walkers will do remote support tickets once they've finished working on migrated users.
Both in and out of office end users will be assigned to floor walkers.
Log sheet to log status of user’s migration will be prrovided to Territory Leads and Service Delivery Managers at EOB.
Floor walkers will have a USB drive with documnetation and migration tools.
Instructions/reminders
If user is not available during your walk throughs. (Similar to the Business cards that we had for Day 1 DTZ/CW Integration)
leave setup instructions that include a call back number
Verify that all configurations has been completed for their assigned users
Technician to enter approximate amount of time to resolve issues
If you are unable to resolve the issue in approximately 20 minutes
| It must include “Email Migration Issue” in the short description |  |  | It must include "EMAIL MIGRATION Issue" in the short description
| Ticket must be assigned to 4 – Project Unity |  |  | Ticket must be assigned to 4 - Project Unity
7:50am | Floor Walkers |  | Contact assigned end user
If your end user is not at their desk - leave set up instructions hand out
If your end user is there follow your customer interaction script
Conitnue to process your end user list
12:00pm | Floor Walkers |  | Turn in checklists
Continue migration rounds
| Territory leads | service Desk Rep, project rep , SDM | Mid-day Huddle
Assess migration progress and make adjustments
|  | Service Desk Rep | Revise instrutions to desk
|  | Territory lead | Revise instructions to floor walkers
3:30pm | Floor Walkers |  | Continue processing end user migration list
If time allows revisit migrated uses for final check
Turn in final checklist
Mark/Identify users for next day's migration
5:00pm | territory leads | service Desk Rep, project rep, floor walkers | End of day Huddle
review issues encountered
make adjustments to next day activity as needed
review what's coming up for next day
| territory leads | service desk rep | create end of day reports

## Migration Team
Project Team - Daily requirements
Time | Owner | Action
6:30am | Project team | Site Services will need a list of successful and failed migrations prior to start on business. | must have for velocity
User name
location
active sync enabled
shared mailboxes
disabled user mailboxes
7:00am | Project Rep | Attends daily meeting for questions/feedback etc. (morning huddle)
12:00pm | Project Rep | Attends daily meeting for questions/feedback etc. (midday huddle)
5:00pm | Project Rep | Attends daily meeting for questions/feedback etc. (end of day huddle)
NOTE: Project team will have an open bridge so that Teams can join at their respctive times

## Pre-Work
Migration Pre work checklist
Open Items | Owner | Date due
Get floor plans per office | Vince | T-2
| Shane | T-2
| Rodney | T-2
create schedule of techs participation | Territory Leads | T-3
make genius bar assignments | Territory Leads | T-2
Get bridge phone number for SWAT team |  | T-1
create user migration checklist | Territory Leads | T-3
Tijuan has model
create set up instructions - leave behind | Territory Leads | T-2
Print "how To" documents for hand outs | Territory Leads | T-1
Tijuan has model
Post Service Desk phone number and email for any additional help. | territory leads | T-1
| Post service desk phone number and email | territory lead
Coordinate with Office/Business Managers how to group users for migration schedule | Vince | T-5
| Shane | T-5
| Rodney | T-5

## Scripts
Customer interaction:
· When greeting a migrated user these are the questions that the floor walker must ask.
· Good morning, your email was migrated last night. I am checking to see if your email is working for you?
· Have you logged into to Outlook this morning?
· Yes: Is everything work fine for you?
· What credentials did you use? CW, DTZ, CT?
· Are you getting email?
· Does your email signature look OK?
· Have you configured email on your phone and/or mobile device?
o Yes: That is great news!
o Remember to double check your email signature
o No: Let me help you with that.
WE NEED A FEW MORE ANALYSIS QUESTIONS
o Are you using more than one mobile device?
o Do you have an iPad or Tablet?
o Do you have email configured on any additional computers?
· No: What else can I help you with?
Where do you check to ensure an incident ticket has been created?

## Appendix
Project Unity Support Documents:
http://www.cushwakemarketing.com/intcomms/Technology/SupportIndex.htm
Project Unity FAQs:
http://www.cushwakemarketing.com/intcomms/Technology/Outlook_Email_FAQs.pdf
Office Floor Plans:
http://floorplans.cassidyturley.com/vd/vd.jsp

## Check List
Project Unity User Migration Checklist
User | Assigned Tecnician | Outlook Configured? | Email Signature? | Outlook Rules? | Shared Mailboxes? | PST Files? | Mobile Devices? | Status | Estimated Setup Time | Ticket # | Notes
Joe Smith |  | Yes | Yes | N/A | N/A | Yes | Yes

## Data Sheet
Outlook Configured? | Email Signature? | Outlook Rules? | Shared Mailboxes? | PST Files? | Mobile Devices? | Status | Estimated Setup Time
Yes | Yes | Yes | Yes | Yes | Yes | Complete | 15 Min.
No | No | No | No | No | No | In Progess | 30 Min.
|  | N/A | N/A | N/A | N/A | Awaiting User | 45 Min.
60 Min.
60+ Min.